## Sprint Tracker
PromtEval - Sprint Tracker (Mon 3 Aug - Fri 7 Aug 2026)
Working hours/day (930-430, 45 min lunch): |  | 6.25
Total capacity (5 days):
Total estimated hours (all tasks):
Must-have hours:
Stretch hours:
PBI | Priority | Task ID | Task | Est (h) | Day | Status | DoD
PBI-0 Spec-Driven Dev Artifacts | Must | T0.1 | Write spec.md (user story, goals, non-goals, acceptance criteria) | 1 | Mon 3 Aug | Not Started | spec.md exists and clearly states the user story, what's in scope, what's out of scope, and the exact numbers that count as a successful test run.
PBI-0 Spec-Driven Dev Artifacts | Must | T0.2 | Write plan.md (architecture, data contracts, judge prompt design, decisions) | 1 | Mon 3 Aug | Not Started | plan.md exists and every open design question has a real decision written down, not left blank.
PBI-0 Spec-Driven Dev Artifacts | Must | T0.3 | Write tasks.md | 0.5 | Mon 3 Aug | Not Started | tasks.md exists and breaks every PBI into small tasks specific enough that nobody has to ask 'what do you mean' before starting one.
PBI-0 Spec-Driven Dev Artifacts | Must | T0.4 | Stakeholder review of spec/plan/tasks; refine and sign off | 0.5 | Mon 3 Aug | Not Started | Someone has actually read spec.md, plan.md, and tasks.md and said 'yes, build this' - silence doesn't count as approval.
PBI-1 Project Setup & Environment | Must | T1.1 | Initialise Python project, repo, lint config, virtualenv | 1 | Mon 3 Aug | Not Started | Running the install command works with no errors, and the linter (ruff) reports zero problems.
PBI-1 Project Setup & Environment | Must | T1.2 | Configure env vars for provider API keys (.env) | 0.5 | Mon 3 Aug | Not Started | .env.example lists all three required keys (OpenRouter, Gemini, Groq) with no real secrets inside it, and the real .env file is excluded from git.
PBI-1 Project Setup & Environment | Must | T1.3 | Define core Pydantic schemas per plan.md's data contracts | 1.5 | Mon 3 Aug | Not Started | Every data shape from plan.md (EvalRun, LLMCallResult, etc.) exists as a schema, and each one can successfully load a small hand-written sample without crashing.
PBI-2 Prompt Variant Input & Rendering | Must | T2.1 | Finalise EvalRun input JSON format + example input file | 1 | Tue 4 Aug | Not Started | A real example JSON file exists with multiple prompt variants and test cases, and it loads successfully into the EvalRun schema with no errors.
PBI-2 Prompt Variant Input & Rendering | Must | T2.2 | Build the template renderer | 1.5 | Tue 4 Aug | Not Started | Given one prompt variant and one test case, the renderer returns the template with every {blank} correctly replaced by the real value.
PBI-2 Prompt Variant Input & Rendering | Must | T2.3 | Unit tests: full matrix + missing-variable error case | 1 | Tue 4 Aug | Not Started | Tests exist and pass proving every variant/test-case combo renders correctly, and that a missing variable produces a clear, readable error instead of a raw crash.
PBI-3 Multi-LLM Execution Engine | Must | T3.1 | Integrate litellm against OpenRouter, Gemini, Groq | 2 | Tue 4 Aug | Done | One function can send a prompt to any of the three providers (OpenRouter, Gemini, Groq) just by changing the model name string.
PBI-3 Multi-LLM Execution Engine | Must | T3.2 | Build async parallel runner (asyncio.gather + Semaphore) | 2 | Wed 5 Aug | Done | Multiple calls fire at the same time instead of one-by-one, and the number running at once never goes above the concurrency limit.
PBI-3 Multi-LLM Execution Engine | Must | T3.3 | Capture input/output tokens + latency per call | 1 | Wed 5 Aug | Done | Every successful call's result includes the real input token count, output token count, and how many milliseconds it took.
PBI-3 Multi-LLM Execution Engine | Must | T3.4 | Add retry/backoff; populate error field on final failure | 1 | Wed 5 Aug | Done | A temporary failure (like a rate limit) gets retried automatically with increasing wait times; if it still fails after retries, the result's error field is filled in instead of the program crashing.
PBI-4 LLM Judge Evaluation Engine | Must | T4.1 | Write the judge prompt template | 1 | Wed 5 Aug | Done | The judge prompt template exists and includes the rubric, the candidate answer, and clear instructions to return only JSON with a score and reasoning.
PBI-4 LLM Judge Evaluation Engine | Must | T4.2 | Send judge prompt to judge model (temp 0); validate against JudgeResult | 1.5 | Wed 5 Aug | Done | A real judge call returns a score from 1-5 plus reasoning text, and it loads correctly into the JudgeResult schema.
PBI-4 LLM Judge Evaluation Engine | Must | T4.3 | Handle judge parse failures (retry once, fallback score=0) | 1 | Thu 6 Aug | Done | If the judge's response isn't valid JSON, the program asks again once; if it still fails, the result gets a score of 0 and a 'parse failure' reason instead of crashing.
PBI-4 LLM Judge Evaluation Engine | Must | T4.4 | Unit tests with mocked judge responses | 1 | Thu 6 Aug | Done | Tests exist and pass for three cases: a valid JSON response, a broken JSON response, and a JSON response wrapped in markdown formatting.
PBI-6 Scoring, Ranking & Recommendation | Must | T6.1 | Aggregate into VariantScore + weighted_score | 1.5 | Thu 6 Aug | Done | Each prompt variant gets one combined score built from its average quality, cost, and speed, using the weighting formula from plan.md.
PBI-6 Scoring, Ranking & Recommendation | Must | T6.2 | Recommendation generator with rationale | 1.5 | Thu 6 Aug | Done | The program picks exactly one winning variant and writes a plain-English reason for why each other variant scored lower (quality, cost, or speed).
PBI-6 Scoring, Ranking & Recommendation | Must | T6.3 | Report formatter (CLI table + optional Markdown/JSON) | 1 | Thu 6 Aug | Done | Running a report prints a readable ranked table in the terminal and also saves the full results to a JSON file.
PBI-9 CLI Orchestrator | Must | T9.1 | Build cli.py entry point: prompteval run <input.json> [--judge-model] [--concurrency] [--timeout] [--format] | 1.5 | Thu 6 Aug | Done | Typing 'prompteval run <file>' in a real terminal works as an actual command, and passing --judge-model/--concurrency/--timeout/--format changes its behavior instead of being ignored.
PBI-9 CLI Orchestrator | Must | T9.2 | Wire pipeline: load input -> render -> execute -> judge -> score -> report | 1 | Thu 6 Aug | Done | One single command runs the entire tool start to finish -- load the file, render prompts, call the AI, judge the answers, rank them, and save a report -- with no separate scripts needed.
PBI-8 End-to-End Testing & Docs | Must | T8.1 | Full E2E run on one real task through all three providers | 1.5 | Fri 7 Aug | Done | Running the tool for real - 3 prompt variants x 5 test cases against all three providers - produces a complete report with no crashes.
PBI-8 End-to-End Testing & Docs | Must | T8.2 | Write README.md | 1 | Fri 7 Aug | Done | README.md lets someone install the tool, set up their API keys, and run their first evaluation using only the instructions in that file.
PBI-8 End-to-End Testing & Docs | Must | T8.3 | Final bug fixes/polish from E2E run | 1.5 | Fri 7 Aug | Done | Every issue found during the real end-to-end run in T8.1 has been fixed and re-tested.
PBI-10 Interactive Setup Wizard | Extra | T10.1 | Add `prompteval init` -- asks for task name, prompt variants, test cases, and rubric in the terminal, then saves a real input file | 1.5 | Tue 4 Aug | Done | Answering the terminal questions produces a real input file that `prompteval run` can load and execute with no manual edits needed.
PBI-11 AI-Generated Quickstart | Extra | T11.1 | Add `prompteval quickstart` -- AI generates a random task (or uses one you type) plus 5 test cases; user types 3 prompts; the evaluation runs immediately with no separate file/run step | 2 | Tue 4 Aug | Done | Running the command with no pre-made file, answering only the task and 3 prompts, produces a real ranked report -- proven live with a genuine AI-generated task, 5 generated test cases, and a real evaluation run.
PBI-11 AI-Generated Quickstart | Extra | T11.2 | Make quickstart the default when `prompteval` is run with no subcommand (or only flags) | 0.5 | Tue 4 Aug | Done | Typing plain 'prompteval' (or 'prompteval --judge-model x') with no subcommand at all starts the quickstart flow directly; 'prompteval run <file>' and 'prompteval init' still work exactly as before.
PBI-12 Friendly Help & Onboarding | Extra | T12.1 | Add `prompteval /help` (also `help`/`-h`/`--help`) -- a warm, example-filled guide instead of argparse's terse default; add a clear message instead of a crash when no API key is configured at all | 1 | Wed 5 Aug | Done | Typing 'prompteval /help' in a real terminal (PowerShell, confirmed) prints a full walkthrough. Running any real command with zero API keys set prints a clear fix-it message and exits cleanly instead of crashing deep inside a network call.
PBI-13 Single-Prompt Improvement Mode | Extra | T13.1 | Add `prompteval improve` -- asks for ONE prompt only (no separate context question), AI generates 3 realistic scenarios from the prompt's own wording and actually runs it against them, then returns a strict score (1-5) + reasoning + a rewritten, improved prompt (structured JSON, not prose) | 2.5 | Wed 5 Aug | Done | Running the real command with just a prompt (no context asked) produces a real 1-5 score, reasoning grounded in real outputs, and a genuinely rewritten prompt, saved to a real markdown file -- confirmed live.
PBI-14 Double-Click Run Button | Extra | T14.1 | Add 'Run PromtEval.cmd' -- double-click launches quickstart with no venv activation and no flags needed, stays open afterward so results are readable | 1 | Wed 5 Aug | Done | Double-clicking (simulated via a real piped PowerShell invocation) launches the tool, completes a real run, and the window stays open on 'Press any key to continue' instead of vanishing.
PBI-14 Double-Click Run Button | Extra | T14.2 | Bug fix found via the run button: a stray BOM character injected by PowerShell's stdin piping made a 'blank' wizard answer look non-empty, silently skipping AI task generation | 0.5 | Wed 5 Aug | Done | Re-running the same real scenario after the fix shows a proper AI-generated task name instead of an empty/garbled one; added a regression test using a real BOM character so this can't silently regress.
PBI-15 Change Default to Improve | Extra | T15.1 | Change the no-subcommand default (bare 'prompteval' and the double-click .cmd) from quickstart to improve, since single-prompt scoring turned out to be the actually wanted default flow | 0.5 | Wed 5 Aug | Done | Bare 'prompteval' and double-clicking 'Run PromtEval.cmd' both now go straight into the improve flow (asks for one prompt, returns score + rewrite) -- confirmed with two separate live runs. 'quickstart'/'init'/'run' still work unchanged when named explicitly.
PBI-16 Interactive Terminal Menu | Extra | T16.1 | Add an arrow-key menu (questionary) shown when no subcommand is given, replacing the direct default -- lets the user pick Improve/Quickstart/Init/Run/Help/Exit without knowing a command name; existing flags are preserved and applied to whatever gets picked | 1.5 | Thu 6 Aug | Done | Running bare 'prompteval' shows a real arrow-key menu; picking an option runs that exact flow. 12 dedicated tests cover every choice including Ctrl+C/Esc and looping back after Help.
PBI-16 Interactive Terminal Menu | Extra | T16.2 | Bug found via live testing in Git Bash: questionary's arrow-key menu crashes outright in terminals without a real Windows console buffer (Git Bash/mintty, confirmed live) -- added a graceful numbered-list fallback via input() instead of a raw crash | 1 | Thu 6 Aug | Done | Re-ran the exact same real scenario in Git Bash after the fix: the fallback numbered menu renders, accepts a real answer, and a full menu-to-improve run completes end-to-end with a real score + rewrite -- confirmed live, not just mocked.
PBI-16 Interactive Terminal Menu | Extra | T16.3 | User feedback: menu's Help option just repeated the generic /help install guide, not useful in context; 'Build a reusable input file'/'Run an existing input file' choices were unclear. Reworded all 4 main choices to be self-explanatory and added a menu-specific MENU_HELP_TEXT explaining exactly what each option does | 1 | Thu 6 Aug | Done | Selecting Help from the real menu (confirmed live) now explains each option in plain terms with a concrete example, instead of repeating the install/API-key guide.
PBI-5 Cost & Latency Calculation | Stretch | T5.1 | Build pricing table ($ per input/output token) | 1 | Fri 7 Aug | Not Started | A pricing table exists listing $ per input token and $ per output token for every in-scope model.
PBI-5 Cost & Latency Calculation | Stretch | T5.2 | Compute cost_usd per call/variant | 1 | Fri 7 Aug | Not Started | Given a call's real token counts, the calculated dollar cost matches what you'd get doing the multiplication by hand.
PBI-7 Error Handling & Reliability | Stretch | T7.1 | Confirm partial failures never drop completed results | 1 | Unscheduled (if time remains) | Not Started | If some calls in a batch fail, the finished ones are still included in the final report - nothing gets thrown away.
PBI-7 Error Handling & Reliability | Stretch | T7.2 | Add explicit per-provider timeout handling | 1 | Unscheduled (if time remains) | Not Started | A call that hangs past the timeout limit gets cancelled and recorded as a timeout error, instead of hanging forever.